## Sheet1
Week | Focus | Expected Deliverable | Evidence Artifact | Status
1 | Environment setup + repo init | SQL Server Developer Edition installed; Python environment created; repo initialized | /setup/install_log.md | Completed
2 | Execution plan extraction + prototype | Prototype reads .sqlplan, extracts RelOp operators | src/scripts/prototype_plan_analyzer.py | Completed
3 | Plan inspection helper + sample plans | Operator inspection script + sample plans stored | src/scripts/inspect_plan_ops.py + plans/*.sqlplan | Completed
4 | Dataset formalization | schema.sql + test_queries.sql with 3 baseline queries | datasets/schema.sql + datasets/test_queries.sql | Completed
5 | Static analyzer v1 | Regex-based SELECT * + non-sargable detection | src/querylens/analysis/static_rules.py
6 | Unit tests for static rules | Automated test cases for static patterns | tests/test_static_rules.py
7 | ANTLR grammar setup | T-SQL grammar integrated, AST produced | /parser/antlr_setup.md
8 | AST visitor extraction | Extract WHERE/JOIN structures | /parser/ast_extractor.py
9 | Execution plan parser v1 | Extract operators + cost metrics | /analyzer/plan_parser.py
10 | Plan rule correlation | Match static flags to runtime ops | /analyzer/correlation_engine.py
11 | Report generator v1 | Plain-text diagnostic output | /reports/sample_report.txt
12 | HTML report generator | Styled report output | /reports/sample_report.html
13 | Expanded test suite | 20 total test queries | /datasets/test_queries.sql
14 | Static analyzer refinement | Additional rule patterns | /analyzer/static_rules.py
15 | Runtime parser refinement | Handle join, sort, hash ops | /analyzer/plan_parser.py
16 | Correlation accuracy testing | Produce correlation_matrix.csv | /artifacts/correlation_matrix.csv
17 | False positive tuning | Updated rule thresholds | /artifacts/validation_log.txt
18 | Usability survey prep | Peer review questionnaire | /artifacts/usability_survey.pdf
19 | Full 30-case evaluation run | All metrics computed | /artifacts/detection_results.json
20 | Performance overhead testing | Timing logs | /artifacts/performance_log.csv
21 | Final integration cleanup | Unified CLI tool | /querylens.py
22 | Documentation writing | User + technical guide | /docs/user_manual.pdf
23 | Buffer week | Bug fixes | Git commit log
24 | Final packaging | Submission bundle | /final_submission/
25 | Demo preparation | Live demonstration script | /demo/demo_script.md